## Sheet1
Date | Application Segment | Flow | Task Name | Description | Status
2022-06-13 | MIddle Tier/ Python | - | Creating the end to end Django Flow | Designing the approver and uploader flow in Django | Done
2022-06-13 | UI | - | Perpwork | HTML, CSS ( and Bootstrap) Layout and JavaScript calls defined | Done
2022-06-13 | UI | Uploader | Design - Uploader Flow | Designing the application based on the emails from Alexios | Done
2022-06-13 | UI | Admin | Design - Admin Flow | Designing the application based on the emails from Alexios | On Going
2022-06-13 | MIddle Tier/ Python | - | Understand the License File | Understand the License File sent across by SPDX | On Going
2022-06-13 | MIddle Tier/ Python | - | Understand the License File | Review and Analyse the Tree Data Structure of the Canonical Format | On Going
2022-06-14 | Backend | - | Understanding the deployment process | List out the various hosting methods | Done
2022-06-14 | Backend | - | AWS Services | List out the AWS services to be used for optimal experience | Done
2022-06-14 | Backend | - | Find the Best SQL Databse for application | Finalized between SQLite and Prostgres | Done
2022-06-14 | MIddle Tier/ Python | All | User - login, register and role creation | Define the model for the user object, create django forms for the same with validations | Done
2022-06-14 | MIddle Tier/ Python | All | User - login, register and role creation | Define validation rules for the form and display error messages | Done
2022-06-15 | UI | All | User - login, register and role creation | Design the UI for user sign-in, registering and forgot password screens | Done
2022-06-15 | Middle Tier/ Python | All | User Session | Provide Authentication and define the session | Done
2022-06-16 | Backend | All | License tables as per version 2 | Define the models for license table | Done
2022-06-16 | Middle Tier/ Python | All | model based form for license upload | design the django form based on the license model | Done
2022-06-16 | Middle Tier/ Python | Approver/ Uploader | user redirect | redirect dashborad based on user role | Done
2022-06-16 | UI | Uploader | license upload feature in uploader dashboard | license upload feature in uploader dashboard | Done
2022-06-16 | Middle Tier/ Python | Uploader | user session management | define user session rules and timeout period | Done
2022-06-17 | Middle Tier/ Python | Uploader | Trigger creation | Trigger to fill model on POST request and save the model object | Done
2022-06-17 | Middle Tier/ Python | Uploader | license view | feature to view all uploaded licenses | Done
2022-06-17 | Backend | - | DB tables structure re-definition | redefine tables based on Mentor Reviews | Done
2022-06-18 | UI | Uploader | License Detail View | Design UI to view individual license Details | Done
2022-06-18 | Middle Tier/ Python | Uploader | License Detail View | Define the view to view license Details and provide dynamic urls for each license | Done
2022-06-18 | ALL | Uploader | Unit Test | Test all views and models done so far | Done
2022-06-18 | ALL | Uploader | Bug Fixing | Fix all bugs found | Done
2022-06-19 | Middle Tier/ Python | Uploader | License Edit Option | Created view to edit License form | Done
2022-06-19 | UI | Uploader | License Edit Option | UI to edit license form | Done
2022-06-19 | Backend | Uploader | License Edit Option | Updating the model for the license data | Done
2022-06-20 | UI | Approver/ Uploader | Table Sorting | Ajax calls to have a responsive table | Done
2022-06-20 | UI | Approver | View uploaded licenses | UI for approver to view uploaded licenses | Done
2022-06-20 | Middle Tier/ Python | Approver | View uploaded licenses | View and functions for approving/rejecting licenses | Done
2022-06-20 | Backend | Approver | View uploaded licenses | Model rendering and DataBase updation | Done
2022-06-20 | UI | Approver | Search for Licenses | UI for approver to view all licenses | Done
2022-06-20 | Middle Tier/ Python | Approver | Search for Licenses | View and functions for searching all licenses | Done
2022-06-21 | UI | Approver | Approve/ Reject Licenses | UI for approver to approve/ reject licenes | Done
2022-06-21 | Middle Tier/ Python | Approver | Approve/ Reject Licenses | View and functions to approve/ reject licenes | Done
2022-06-21 | Backend | Approver | Approve/ Reject Licenses | model and database updation | Done
2022-06-21 | Middle Tier/ Python | Uploader | View Rejected Licenses | Updation view to include rejected licenses | Done
2022-06-22 | Middle Tier/ Python | Approver | License Tracking feature | View and functions to view the license tracking | Done
2022-06-21 | UI | Approver | License Tracking feature | UI to view the license tracking details and Ajax calls to search and sort the table | Done
2022-06-22 | Middle Tier/ Python | Uploader | License Tracking feature | View and functions to view the license tracking | Done
2022-06-21 | UI | Uploader | License Tracking feature | UI to view the license tracking details and Ajax calls to search and sort the table | Done
2022-06-22 | UI | Uploader | Dashboard population | View to populate dashboard with license aggregation counts | Done
2022-06-22 | UI | Uploader | Last login changes | Adding a feature to view the changes since last login | Done
2022-06-22 | UI | Approver | Dashboard population | View to populate dashboard with license aggregation counts | Done
2022-06-22 | UI | Approver | Last login changes | Adding a feature to view the changes since last login | Done